## Risk Management Table
Risk Description | Category | Impact | Likelihood | Prevention Strategy (Plan A) | Contingency Strategy (Plan B)
Core player movement and jumping does not feel fun or responsive | Design / Scope | High | Medium | Create an early vertical slice and conduct movement-focused playtests | Replace with a simpler, proven movement system (basic acceleration + jump)
Physics or collision bugs block player progression | Technical | High | Medium | Use engine default physics and avoid custom collision code early | Simplify levels to static platforms and disable advanced physics
Level design takes longer than planned due to iteration | Schedule / Scope | Medium | High | Greybox levels and limit First Playable to one level | Cut decorative elements and reduce platform variety
Solo developer workload causes missed deadlines or burnout | Personnel | High | Medium | Plan realistic work hours and limit tasks per sprint | Reduce scope by cutting non-essential features or polish
Visual assets look inconsistent or low quality | Art / Quality | Medium | Medium | Use placeholder assets with a consistent style guide | Switch to a minimalist visual style using simple shapes
Build or export failure before milestone submission | Technical / Delivery | High | Low | Create test builds at the end of every sprint | Submit recorded gameplay footage as proof of functionality
Feature creep expands scope beyond original plan | Scope / Management | High | Medium | Lock feature list after First Playable milestone | Remove secondary mechanics such as enemies or moving platforms